## Fact Pattern
id | Fact
0 | JITA and the Federal Highway Administration, a DOT component, executed the contract for road work in Mesa Verde National Park in Colorado on February 4, 2021.
1 | The completion date for the schedule A work, reconstructing a roadway 'loop,' was June 15, 2021.
2 | Work on at least one of the options could not begin until the primary work was finished, and all work including the options was to be completed by September 6, 2021.
3 | The contract contained provisions for weather delays, but the parties do not direct us to any indication that the work was limited to certain seasons of the year.
4 | The contract included both 'disincentive deductions' from the contract price if JITA did not timely complete the schedule A work and a table of graduated 'liquidated damages' starting at $1600 per day for late completion of the entire contract.
5 | The agency issued the notice to proceed on or about March 8, 2021.
6 | Between March 4 and April 18, JITA submitted multiple project schedules that showed substantial completion of the schedule A work between three and twenty-eight days past the required date of June 15.
7 | Problems arose in April 2021 relating to pouring concrete.
8 | After correspondence and meetings, the agency sent JITA a letter of concern on May 19.
9 | Two days later, JITA submitted a schedule showing the schedule A work ending on August 24, sixty-four days late.
10 | JITA responded to the agency's letter of concern on June 10, 2021 (fifteen days late).
11 | On June 17, 2021, two days after the interim completion date of the schedule A work, the contracting officer's representative wrote to JITA that 'all concrete placed to date on Schedule A is rejected and must be removed and replaced.'
12 | On July 1, 2021, a JITA representative emailed the agency's project manager noting that the agency had begun to record (but not actually to collect) price deductions for late completion of the schedule A work in approving progress payments.
13 | The agency's project manager responded to the July 1 email by letter the same day.
14 | On July 7, 2021, the agency issued a second letter of concern and requested another corrective action plan within seven days.
15 | JITA responded in a two-page letter on July 14.
16 | Meetings and correspondence about achieving progress on the project continued in the summer.
17 | JITA's schedule dated August 26, the last update that JITA would submit until late October 2021, showed completion of the schedule A work on October 27, 2021, which was 134 days past the interim completion date for that work and fifty-one days after the contract's final completion date.
18 | The last progress payment processed and paid by DOT was for work accepted by DOT through August 31, 2021.
19 | On September 24, eighteen days after the final completion date of September 6, the agency issued a show cause notice.
20 | JITA responded, through counsel, on October 7, 2021 (three days late), by letter styled as a 'confidential settlement offer.'
21 | JITA demobilized on October 29, 2021.
22 | DOT terminated the contract for default on November 10, 2021.
23 | A tender agreement executed in March 2022 by DOT and JITA's surety recites that the surety paid DOT, among other amounts, disincentives of $399,600 and liquidated damages of $416,000 under the contract.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Determining relevance of evidence related to contract performance. | The evidence regarding the timeline of contract execution, completion dates, and delays is relevant to assess whether JITA met the contractual obligations. | ['The timeline of events directly relates to the performance of the contract.', "Evidence of delays and communications provides context for the agency's actions."] | ['Some evidence may be seen as cumulative or not directly related to the legal issues at hand.'] | admissible | [0, 1, 2, 4, 6, 8, 10, 12, 14, 16]
FRE 402 | General Admissibility of Relevant Evidence | Admissibility of evidence that is relevant to the case. | All evidence presented regarding the contract and its execution is relevant and should be admissible unless otherwise excluded. | ['All evidence is relevant to the issues of contract performance and breach.', 'No specific exclusions apply to the evidence presented.'] | [] | admissible | [0, 1, 2, 4, 6, 8, 10, 12, 14, 16]
FRE 404 | Character Evidence; Crimes or Other Acts | Use of prior conduct to establish a pattern of behavior. | Evidence of JITA's past performance on similar contracts may be relevant to establish a pattern of behavior regarding timely completion. | ['Past performance can show a pattern that is relevant to the current case.', 'It may help establish intent or knowledge regarding contract obligations.'] | ['Such evidence may be prejudicial and not directly relevant to the specific contract in question.'] | depends | []
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Determining whether statements made in correspondence are hearsay. | Correspondence between JITA and the agency may be considered hearsay unless it falls under an exception. | ['Statements made in the course of business may be admissible as non-hearsay.', 'They may also be admissible to show the state of mind of the parties.'] | ['If offered to prove the truth of the matter asserted, they may be considered hearsay.'] | depends | [8, 10, 12, 14]
FRE 803 | Exceptions to the Rule Against Hearsay | Exceptions that allow certain hearsay statements to be admissible. | Certain statements made in the course of business or during the performance of the contract may be admissible under exceptions to the hearsay rule. | ['Business records may be admissible if they were made at or near the time of the event.', 'Statements made for the purpose of fulfilling contractual obligations may be relevant.'] | ['Some statements may not meet the criteria for business records or other exceptions.'] | depends | [8, 10, 12, 14]
FRE 1001 | Definitions That Apply to This Article | Defining what constitutes a writing or recording. | Documents related to the contract, including emails and letters, must be properly authenticated to be admissible. | ["If properly authenticated, these documents can serve as evidence of the parties' communications and intentions."] | ['If the documents cannot be authenticated, they may be inadmissible.'] | depends | [8, 10, 12, 14]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Enforceability of Completion Dates | DeVito v. United States, 413 F.2d 1147 (Ct. Cl. 1969) | Whether the government waived its right to enforce the completion date due to contractor's continued performance. | If the government allows a contractor to continue performance past a due date without terminating the contract, it may forfeit its right to terminate for default, provided the contractor has not abandoned performance and a reasonable time has passed. | DOT did not waive the completion date as it documented disincentive deductions immediately after JITA missed the interim completion date and issued a show cause notice shortly after the final completion date. | ['DOT began documenting disincentive deductions promptly after JITA missed the interim completion date.', 'The show cause notice indicated that DOT was still considering its options regarding the contract.', 'JITA did not submit a pay application for work performed after the final completion date.'] | ["JITA may argue that DOT's actions indicated acceptance of late performance.", "JITA could claim that the agency's requests for schedules implied a waiver of strict adherence to the completion dates."] | applies | [1, 2, 3, 4, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19]
Disincentive Deductions | Contract terms and FAR guidance | Whether disincentive deductions are enforceable under the contract. | Disincentive deductions are enforceable if the contract explicitly states the conditions under which they apply. | The contract included provisions for disincentive deductions for failure to meet the interim completion date, which were applicable despite the presence of option work. | ['The contract clearly states that failure to meet the interim completion date will result in disincentive deductions.', 'The language of the contract indicates that disincentives apply regardless of whether options are awarded.'] | ['JITA may argue that disincentives should not apply since Schedule A was not the only award.', "JITA could claim that the contract's language is ambiguous regarding the application of disincentives."] | applies | [4, 5, 10, 11, 12, 19]
Burden of Proof in Default Termination | DCX, Inc. v. Perry, 79 F.3d 132 (Fed. Cir. 1996) | Who bears the burden of proof in justifying a termination for default. | The agency bears the burden to show that the contractor was in default at the time of termination. | DOT must demonstrate that JITA failed to meet the completion date and that this failure justified the termination. | ["DOT's complaint alleges that JITA did not complete the work by the final completion date.", "The agency's documentation of disincentives supports its claim of JITA's default."] | ['JITA can argue that its delays were excusable due to agency actions.', 'JITA may present evidence that it was making reasonable efforts to complete the work.'] | uncertain | [1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19]