## Fact Pattern
id | Fact
0 | These appeals are before us following a five-day hearing that was conducted in March 2023 before Judge Jerome M. Drummond.
1 | During post-hearing briefing, Judge Drummond unexpectedly passed away.
2 | After a new presiding judge was assigned to the appeals, the parties elected to rely on the transcripts of the March 2023 hearing rather than again to present witnesses for live testimony before the new presiding judge.
3 | In CBCA 6149, appellant, Alares Construction, Inc. (Alares), seeks to recover damages of $1,691,701.85 (a figure that has been revised several times during the course of litigation) for delays and changes on a construction project at a Department of Veterans Affairs (VA) medical center but with a reduction to its claimed general conditions costs to account for its settlement and release of some of its earlier claims under this contract.
4 | With the reduction, Alares tells us, the claim is approximately $1.5 million.
5 | Alares asserts that the VA caused all 765 days of delay on this project, but it seeks to recover extended general conditions for only 653 of those days.
6 | On April 28, 2016, the VA awarded a firm-fixed-price construction contract (contract VA241-16-C-0037 (the contract)) to Alares for the replacement/relocation of the deficient Intensive Care Unit (ICU) at the Providence VA Medical Center in Providence, Rhode Island, for a lump-sum price of $7,753,880.20.
7 | The project required the construction of a two-story addition to an existing building.
8 | Alares was to connect the addition to the existing building through an elevated hallway, which would run between the second floor of the addition and a second-floor opening in the existing building.
9 | Contract duration was to be 425 calendar days from the date that the VA issued the Notice to Proceed (NTP).
10 | The VA issued the Notice to Proceed on June 3, 2016, with an expected completion date within 425 calendar days (or August 2, 2017).
11 | Period 1 covers the 212-day period of time running from June 3, 2016, through January 13, 2017.
12 | Alares’ Chief Executive Officer (CEO), Donald Maggioli, developed the original construction schedule for the project with the assistance of one of Alares’ construction managers.
13 | Alares’ June 3, 2016, baseline schedule projected substantial completion of the project by August 2, 2017.
14 | By the time that Alares issued another schedule update (no. 4) on January 13, 2017, the projected substantial completion date had moved to September 5, 2017.
15 | The critical path of performance initially, and logically, focused on Alares’ set-up of the construction site and its initial performance activities.
16 | The parties agree that, during the initial months of the project, there were no critical path delays.
17 | By October 2016, the critical path had turned towards the need to complete foundational work, which was necessary to allow Alares to begin erecting structural steel.
18 | Alares commenced excavation work on August 22, 2016.
19 | Alares had planned on completing foundation work on October 27, 2016, but did not do so until November 1, 2016, four days later than planned.
20 | Alares asserts that this four-day delay was caused by the discovery of unforeseen underground piping that was not shown on the contract drawings.
21 | The VA provided Alares with a new sewer route location.
22 | The VA indicated, in a progress meeting on November 3, 2016, that it would waive the requirement for twenty-eight days of curing and allow steel erection to begin early if the results of a test of strength were acceptable.
23 | The VA received a positive test result on November 7, 2016, and Alares began steel erection on November 9, 2016.
24 | Alares asserts that the remaining thirty days of critical delay during this period resulted, in large part, from coordination issues in resolving conflicts in the specifications relating to MEP work, including fire protection and medical gas systems, for which Alares asserts the VA is responsible.
25 | Alares submitted RFI 005 on October 20, 2016, with preliminary questions about requirements for the coordination drawings that its subcontractor, Delta Mechanical Contractors (Delta Mechanical or Delta), was preparing.
26 | Alares’ subcontractor, Delta, met with the A/E and the VA on November 10, 2016, and the A/E and the VA indicated that they would consider Alares’ request to drop the ceilings on an as-needed and room-by-room basis once Alares submitted final coordination drawings.
27 | Alares submitted the initial Delta-created coordination drawings to the VA on December 20, 2016, while indicating that Delta still needed the A/E’s revised plans as discussed in the VA’s original response to RFI 005.
28 | Alares submitted a revision to RFI 005 on December 22, 2016.
29 | On February 10, 2017, Alares submitted its second revision to RFI 005.
30 | After resolving what it called 'issues with submission,' and participating in a conference call with Delta and the VA, the A/E, on or before February 23, 2017, issued Bulletin 3 and its response to the second revision of RFI 005, resolving the MEP coordination conflicts.
31 | Alares also asserted that, beyond the four days of delay previously discussed for which the VA assumes responsibility, additional critical delays in Period 1 were caused by the continuing effects of unforeseen underground steam lines, unforeseen underground steel piping, and defective design drawings.
32 | The parties dealt with these issues before Alares completed its foundation work on November 1, 2016.
33 | The record reflects that any critical path delays (beyond the four-day period associated with laying the foundation) related to Alares’ slow progress on steel erection, decking, welding, and detailing.
34 | Alares has identified no viable defects in drawings or with VA coordination and assistance that would have slowed Alares’ steel work once it began.
35 | Throughout Period 1 and into Period 2, the VA was complaining that the schedule was slipping for reasons that the VA did not understand.
36 | On January 9, 2017, Mr. Boyle, the VA COR, complained that '[a]fter reviewing [the] latest schedule, dated 12/8/2016, this morning I have to reiterate my concern that the schedule is sliding on the ICU project.'
37 | The VA issued a cure notice on August 2, 2017, declaring that Alares was in default on the contract for failing to meet the contractual completion deadline of August 2, 2017.
38 | On August 11, 2017, Alares responded with an updated schedule identifying an anticipated substantial completion date of December 1, 2017.
39 | On February 10, 2020, Alares submitted a claim to the VA contracting officer on February 10, 2020, seeking payment of $7344.70 (now reduced to of $6538.24) for the cost of reinstalling structural supports.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Definition of hearsay and its exceptions. | The transcripts of the March 2023 hearing may contain statements made by witnesses that could be considered hearsay if offered for the truth of the matter asserted. | The transcripts may be admissible under the residual exception to hearsay if they meet certain criteria, such as being trustworthy and having equivalent circumstantial guarantees of trustworthiness. | If the statements in the transcripts are offered to prove the truth of the matters asserted, they may be considered hearsay and thus inadmissible unless an exception applies. | depends, as it will depend on whether the statements in the transcripts meet the criteria for an exception to the hearsay rule. | [2, 3]
FRE 1002 | Requirement of the Original | Admissibility of secondary evidence when the original document is not available. | The parties are relying on transcripts instead of live testimony, which raises the issue of whether the transcripts can serve as the original evidence of what was said during the hearing. | The transcripts are the official record of the hearing and can be considered the best evidence of the proceedings that took place. | If the transcripts are incomplete or inaccurate, they may not be admissible as the original evidence of the hearing. | admissible, as they are the official transcripts of the hearing and are likely to be considered the best evidence available. | [2, 3]
FRE 402 | General Admissibility of Relevant Evidence | Relevance of evidence presented in the appeals. | The evidence presented in the appeals, including the claims for damages and delays, must be relevant to the issues at hand. | The evidence is directly related to the claims and defenses in the appeals, making it relevant to the determination of damages and liability. | If any evidence is deemed irrelevant to the specific claims being made, it may be excluded. | admissible, as the evidence appears to be relevant to the issues being litigated in the appeals. | [3, 4, 5, 6]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Balancing the probative value of evidence against potential prejudice. | The court must consider whether the evidence presented, particularly regarding delays and damages, is more prejudicial than probative. | The evidence is necessary to establish the claims and defenses, and its probative value outweighs any potential prejudice. | The evidence may confuse the issues or mislead the jury if it is overly complex or if it introduces collateral issues. | depends, as the court will need to weigh the probative value against any potential for prejudice or confusion. | [4, 6, 7, 8]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Suspension of Work Clause | FAR 52.242-14 | Whether the contractor is entitled to an adjustment for delays caused by the government. | If the performance of work is suspended, delayed, or interrupted by an act of the Contracting Officer, an adjustment shall be made for any increase in the cost of performance of the contract, excluding profit, caused by the unreasonable suspension, delay, or interruption. | The Board found that the VA was responsible for certain delays, which allowed Alares to claim compensation under the suspension of work clause. | ["The VA's actions caused delays that affected the critical path.", 'Alares was entitled to an adjustment for costs incurred due to these delays.'] | ["No adjustment shall be made for delays caused by the contractor's own fault.", "The contractor must prove that the delays were solely due to the government's actions."] | applies | [11, 12, 13, 14, 15]
Critical Path Method (CPM) Analysis | Construction Contracting Principles | Whether the contractor can recover damages for delays based on a critical path analysis. | To recover for delays, the contractor must establish the critical path of the project and demonstrate how government-caused delays affected activities on that path. | Alares needed to provide a CPM analysis to support its claims for damages due to delays, but its analysis was found lacking. | ['The CPM is a standard method for analyzing delays in construction projects.', "Alares' failure to provide a credible CPM analysis undermined its claims."] | ['The contractor can still recover if it can show that delays were caused by the government.', "The contractor's own delays must be shown to be concurrent with government-caused delays."] | does not apply | [4, 5, 6, 7, 8, 9, 10]
Good Faith and Fair Dealing | Metcalf Construction Co. v. United States | Whether the government breached its duty of good faith and fair dealing in contract performance. | Every contract imposes a duty of good faith and fair dealing in its performance and enforcement, and failure to fulfill that duty constitutes a breach of contract. | Alares claimed that the VA's actions forced it to absorb additional costs and created an adversarial environment, but the Board found no evidence of bad faith. | ["The VA's actions were within its rights under the contract.", 'Alares did not provide sufficient evidence of bad faith or unreasonable conduct by the VA.'] | ["The VA's actions were perceived as adversarial and unreasonable.", "The VA's funding limitations affected its ability to approve change orders."] | does not apply | [4, 5, 6, 7, 8]
Release of Claims | Modification P00015 | Whether the contractor can pursue claims that were released in a prior settlement. | A release of claims in a settlement agreement precludes the contractor from reviving those claims later. | Alares' settlement of certain REAs included a release of all claims related to those REAs, preventing it from claiming those costs again. | ['The settlement agreement explicitly stated that it constituted full and complete satisfaction of the claims.', 'Alares cannot double-dip by claiming costs already settled.'] | ['Alares argues that the settlement did not cover all costs and that it should be allowed to claim them.', 'The contractor may argue that the release was not intended to cover all future claims.'] | applies | [4, 5, 6, 7, 8]