## Fact Pattern
id | Fact
0 | On May 26, 2011, GSA awarded Wise lease number LNC61075 (the contract) for leased facilities in Hickory, North Carolina.
1 | The contract specified a ten-year term, the first five of which were firm (the firm term), which meant that the contract could not be terminated during the first five years.
2 | Rent was initially established at $36,241.29 per month for the firm term, then amended to $37,252.96 per month.
3 | The contract involved a 'build to suit' project, designed and constructed specifically for the mission of the tenant agency, SSA.
4 | The facility, a customer service center for the local community, was a brand new, LEED certified, single-story office building, with the SSA as the sole tenant.
5 | Specifications for constructing 'build to suit' facilities for the SSA were detailed and extensive due to the high customer volume and public-facing nature of its day-to-day mission.
6 | The contract required Wise to lease to GSA '[a] total of 14,950 rentable square feet (RSF) of space on the first floor of a building to be constructed on Parcel Number 370213144561 in Southgate Corporate Park' and 'seventy-eight (78) onsite, surface parking spaces for the exclusive use of Government employees and patrons.'
7 | In addition to providing office space and parking spaces for the tenant agency, the terms of the contract required Wise to furnish to the Government, as part of the rental consideration, the following: All labor, materials, equipment, design, professional fees, permit fees, inspection fees, utilities, construction drawings (including, without limitation, plans and specifications), construction costs and services and all other similar costs and expenses associated with making the space, common areas, and related facilities ready for occupancy in accordance with the requirements of this lease and the Government's final construction drawings.
8 | The solicitation was expressly incorporated into the contract and contained multiple provisions relevant to this dispute.
9 | The contract contained detailed specifications related to air quality in the facility.
10 | Construction and build-out of the facility were completed in late September 2012—sixteen months after contract award.
11 | The SSA occupied the building on October 5, 2012.
12 | After opening its doors to the public on October 10, 2012, the facility served an average of 2800 customers per month.
13 | In February 2013—four months after moving into their new office—SSA employees raised concerns about an odor in the building.
14 | During the seventeen months that the SSA occupied the building, SSA personnel contacted the Hickory Fire Department eight times due to concerns about the odor.
15 | The record also contains two OSHA complaints, received months apart, describing a long list of physical symptoms experienced by 'SSA staff,' including headaches, nausea, nosebleeds, dizziness, stomach cramps, inability to breathe normally or deeply, bad taste in the mouth, and sinus pain, among other symptoms.
16 | The on-site SSA manager eventually developed an incident log to track occurrences of the odor and any resulting office closures.
17 | Due to the contract's strict requirements for indoor air quality, as well as the disruption to the SSA's mission, the parties began an intense course of investigating, testing, measuring, cleaning, inspecting, and analyzing all key aspects in and around the building to identify the cause of the odor and fix it.
18 | The contracting officer sent Wise a letter stating that 'the Government [was] exercising a redeployment plan and vacating the majority of the premises effective February 24, 2014, due to continuing problems with noxious odors.'
19 | Wise responded to the contracting officer's notice of redeployment on March 4, 2014, taking issue with the contracting officer's reference to 'noxious odors.'
20 | Despite their mutual frustration, the parties continued to perform due diligence on various systems, equipment, and materials in the building to identify or eliminate them as possible odor sources.
21 | Wise's project manager performed a walkthrough inspection of the office.
22 | Wise responded to the contracting officer's 'open items letter' of July 10.
23 | The contracting officer issued Wise a follow-up letter on open items entitled 'Outstanding Items Needed.'
24 | Wise's Continued Efforts to Identify and Remedy the Cause of the Odor.
25 | By letter dated August 22, 2014, GSA terminated the lease for default stating, 'After review of your responses to the deficiency letter . . . and the cure notice . . . the Government has decided to pursue the default language in the lease and seeks to vacate the space as soon as practical.'
26 | Wise was surprised to receive a default termination letter.
27 | The SSA completely vacated Wise's facility on October 22, 2014, though GSA continued to pay rent at a reduced rate through the end of 2014.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Determining relevance of evidence related to the lease and odor issues. | The evidence regarding the lease terms and the subsequent odor complaints is relevant to establish the context of the dispute and the obligations of the parties under the contract. | The evidence directly relates to the performance of the lease and the issues that arose during its execution, which are central to the case. | There may be arguments that some evidence is too remote or not directly related to the specific legal issues at hand. | admissible | [0, 1, 4, 5, 12, 13, 14, 15, 16, 18]
FRE 402 | General Admissibility of Relevant Evidence | Admissibility of evidence that is relevant to the case. | All relevant evidence regarding the lease and the odor complaints should be admissible unless otherwise excluded by law. | The evidence is relevant and not subject to exclusion under any specific rule. | Potential objections may arise regarding the prejudicial impact of certain evidence. | admissible | [0, 1, 4, 5, 12, 13, 14, 15, 16, 18]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Balancing the probative value of evidence against its potential prejudicial effect. | While the evidence is relevant, there may be concerns about its prejudicial impact on the jury, particularly regarding the emotional responses to health complaints. | The probative value of understanding the lease obligations and the odor issues outweighs any potential prejudicial effect. | The evidence may evoke strong emotional reactions from the jury, potentially leading to bias. | depends | [12, 13, 14, 15, 16]
FRE 404 | Character Evidence; Crimes or Other Acts | Use of evidence regarding the parties' conduct in relation to the lease. | Evidence of the parties' actions and responses to the odor complaints may be considered character evidence, which is generally inadmissible to prove conduct. | The evidence may be admissible to show the parties' state of mind or to establish a pattern of behavior relevant to the contract's execution. | The evidence may be seen as character evidence that is inadmissible to prove that a party acted in accordance with that character. | depends | [12, 13, 14, 15, 16]
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Determining whether certain statements made by SSA personnel regarding the odor are hearsay. | Statements made by SSA personnel about the odor and their symptoms may be considered hearsay unless they fall under an exception. | If the statements are offered to show the effect on the listener or for a purpose other than the truth of the matter asserted, they may be admissible. | The statements may be considered hearsay if offered to prove the truth of the symptoms experienced. | depends | [12, 13, 14]
FRE 803 | Exceptions to the Rule Against Hearsay—Regardless of Whether the Declarant Is Available as a Witness | Potential exceptions to hearsay for statements made regarding the odor complaints. | Certain statements made by SSA personnel may qualify for exceptions to the hearsay rule, such as present sense impressions or excited utterances. | If the statements were made in the heat of the moment regarding the odor, they may be admissible under the excited utterance exception. | If the statements were made after the fact or in a reflective manner, they may not qualify for an exception. | depends | [12, 13, 14]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Default Termination Standard | Lisbon Contractors, Inc. v. United States | Whether the government had sufficient grounds to terminate the lease for default. | A default termination is a drastic sanction that should only be imposed for good grounds and solid evidence. | The Board found that the government failed to establish a prima facie case for the default termination, as the odor complaints did not constitute a clear violation of contract terms. | ['The contract did not require an odor-free building.', 'Extensive air quality testing showed compliance with contract standards.'] | ['The government argued that the persistent odor constituted a failure to maintain the premises.'] | applies | [13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
Constructive Eviction Doctrine | Common Law Principle | Whether the government could assert constructive eviction as a basis for lease termination. | Constructive eviction occurs when a landlord's actions render the leased premises unfit for the intended use or deprive the tenant of beneficial enjoyment. | The Board found that the government did not establish that Wise's actions rendered the building uninhabitable or that the odor constituted a substantial interference. | ['The building was deemed well-maintained by the contracting officer.', 'The odor was intermittent and did not violate air quality standards.'] | ['The government claimed that the odor significantly disrupted SSA operations.'] | does not apply | [20, 21, 22, 23, 24, 25, 26, 27, 28]
Duty to Mitigate Damages | Restatement (Second) of Contracts | Whether Wise took reasonable steps to mitigate damages after the government vacated the premises. | A party cannot recover damages that could have been avoided by reasonable efforts. | The Board found that Wise had a duty to mitigate its damages but failed to take basic steps to re-let the building, such as posting a 'for rent' sign. | ["The eventual tenant had to research property records to find Wise's contact information.", 'Wise did not provide sufficient evidence of its efforts to find a new tenant.'] | ['Wise argued that it was actively testing the building to ensure safety for future tenants.'] | applies | [29, 30, 31, 32, 33, 34, 35]
Burden of Proof in Mitigation | T.C. Bateson Construction Co. v. United States | Who bears the burden of proof regarding the adequacy of mitigation efforts? | The burden of proof regarding a non-breaching party's failure to mitigate damages rests upon the breaching party who asserts it. | The Board found that the government established a prima facie case that Wise's mitigation efforts were inadequate, shifting the burden to Wise to demonstrate reasonable efforts. | ['The government presented evidence that Wise did not take basic steps to mitigate damages.', "Wise's owner provided vague statements about mitigation efforts."] | ['Wise claimed it was actively working to ensure the building was safe for occupancy.'] | applies | [29, 30, 31, 32, 33, 34, 35]