## Fact Pattern
id | Fact
0 | On May 2, 2016, FHWA awarded Eagle Peak a contract to make improvements along 4.7 miles of Grand Loop Road in Yellowstone National Park, Wyoming, as well as nearby parking areas, trails, and overlooks.
1 | The project was scheduled for three construction seasons with an overall completion date of October 5, 2018, and an interim completion date for the Inspiration Point work of November 15, 2017.
2 | The original contract had an estimated value of $28,049,200.62.
3 | The solicitation also required Eagle Peak to submit bids for certain options, namely options W, X, Y, and Z, which involved additional parking lot, trail, and overlook work at the Brink of the Upper Falls and Uncle Tom’s Point sites.
4 | FHWA exercised these options via a unilateral modification dated July 14, 2016.
5 | The option work totaled $6,536,810.50 and increased the estimated contract value to $34,586,011.12.
6 | The contract contained a Default clause that required an improper termination for default to be converted to one for convenience.
7 | In addition to the winter shutdown periods described above, the contract included the scheduling constraints below.
8 | The contract included a clause precluding the simultaneous closure of the Brink of the Upper Falls and Uncle Tom’s Point sites.
9 | The contract required Eagle Peak to wait a minimum of 180 days after construction of the walls to apply the stone masonry.
10 | The contract included the following requirement as to the performance of clearing and grubbing work at the Canyon Rim sites: Do not cut trees; perform vegetation clearing, grubbing, or other site preparation activities between May 1 and July 31 within the Canyon Rim construction area from Chittenden Bridge to Inspiration Point unless approved by the CO.
11 | FHWA waived this provision in the 2016 season.
12 | The contract also stated that 'seed will not be sown, by the Park Service before September 15 [th] or after June 15 [th] [,]' and required the contractor to '[p]lace mulch over finished slopes to a loose depth of 1/2 inch[,]'.
13 | The contract provided that '[p]lants shall only be planted in the months of April, May, September and October of any given year.'
14 | Pursuant to the contract, Eagle Peak was required to submit an initial construction schedule, a baseline schedule, and an updated construction schedule.
15 | Shortly after contract award, on or around July 22, 2016, Eagle Peak submitted a 'preliminary schedule.'
16 | On October 3, 2016, the CO issued a cure letter to Eagle Peak, stating that the lack of a schedule complying with contract requirements was endangering timely performance.
17 | On October 13, 2016, Eagle Peak submitted another version of its baseline schedule, including a narrative, referred to as revision 5.
18 | By letter dated November 4, 2016, the CO rejected the schedule, stating '[y]ou did not cure the condition that I determined to be endangering the performance of the contract.'
19 | Eagle Peak provided the testimony of Mr. Jason R. Nolting, its scheduling expert, regarding the merit of FHWA’s objections to the October 13, 2016, schedule and whether it should have been accepted.
20 | On November 23, 2016, Eagle Peak submitted yet another baseline schedule (Revision 7).
21 | On January 23, 2017, Eagle Peak submitted another baseline schedule.
22 | On or around January 25, 2017, Eagle Peak’s president submitted a 'recovery schedule,' attempting to respond to the CO’s concerns expressed in her email of January 24, 2017.
23 | The recovery schedule included a narrative report detailing specific project activities and the work to be done, including the estimated number of days, to complete each activity.
24 | In a January 31, 2017, internal memorandum to the 'Contract File,' the CO explained her reasoning for the default termination.
25 | By letter dated February 1, 2017, FHWA terminated Eagle Peak for default pursuant to FAR 52.249-10.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Relevance of evidence regarding contract performance and schedules. | The evidence regarding Eagle Peak's submission of schedules and the CO's responses is relevant to determine whether Eagle Peak met the contractual obligations and whether the termination for default was justified. | The schedules submitted by Eagle Peak and the CO's communications are directly related to the performance of the contract and the justification for termination. | One might argue that the evidence is cumulative or that it does not directly pertain to the specific issues of default termination. | admissible | [12, 13, 14, 15, 16, 17, 18, 19]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Potential for confusion or undue prejudice from the introduction of multiple schedule submissions. | While the evidence is relevant, the sheer number of schedule submissions may confuse the jury regarding the timeline and the nature of the alleged default. | Each submission provides context and demonstrates Eagle Peak's attempts to comply with the contract, which is crucial for understanding the case. | The introduction of multiple schedules could overwhelm the jury and distract from the main issues, leading to confusion. | depends | [12, 13, 14, 15, 16, 17, 18, 19]
FRE 602 | Need for Personal Knowledge | Testimony of Mr. Jason R. Nolting regarding scheduling. | Mr. Nolting's testimony must be based on his personal knowledge of the scheduling issues and the contract requirements. | As a scheduling expert, Mr. Nolting likely has the requisite knowledge to provide relevant insights into the scheduling disputes. | If Mr. Nolting lacks direct involvement with the contract or the specific schedules, his testimony may be challenged for lack of personal knowledge. | admissible | [18]
FRE 701 | Opinion Testimony by Lay Witnesses | Lay opinion testimony regarding the merit of FHWA’s objections. | Mr. Nolting's testimony may include opinions on the reasonableness of the CO's objections to the schedules submitted by Eagle Peak. | His expertise allows him to provide opinions that are helpful to understanding the issues at hand. | If his opinions are deemed to be based on specialized knowledge rather than lay observation, they may be challenged under FRE 702 instead. | depends | [18]
FRE 803(6) | Records of a Regularly Conducted Activity | Admissibility of the schedules as business records. | The schedules submitted by Eagle Peak may qualify as business records, provided they were made at or near the time of the events and kept in the course of a regularly conducted activity. | If the schedules were created and maintained as part of Eagle Peak's regular business practices, they should be admissible as evidence. | There may be questions about the authenticity or the manner in which the records were kept, potentially undermining their reliability. | admissible | [12, 13, 14, 15, 16, 17, 18, 19]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Default Termination Clause | FAR 52.249-10 | Whether the termination for default was justified under the contract. | A termination for default is justified when a contractor fails to prosecute the work with sufficient diligence to ensure completion within the specified time. | The CO determined that Eagle Peak was not prosecuting the work diligently enough to meet the completion date, leading to the termination for default. | ['Eagle Peak failed to submit a compliant schedule, which was deemed critical for timely performance.', "The CO's analysis indicated that Eagle Peak would be late in completing the project."] | ["Eagle Peak submitted multiple schedules and attempted to address the CO's concerns.", 'Expert testimony indicated that the schedules were largely compliant and that the issues raised did not impact the critical path.'] | does not apply | [8, 10, 14, 15, 16, 18, 19, 20, 21, 22]
Conversion of Termination | Contract Default Clause | Whether an improper termination for default should be converted to a termination for convenience. | If a termination for default is found to be improper, it must be converted to a termination for convenience. | The Board found that the termination for default was improper and converted it to a termination for convenience based on the evidence presented. | ["Eagle Peak's schedules demonstrated an understanding of the work and a plan to complete it.", "The CO's reasons for termination were not reasonable given the circumstances."] | ["The CO believed that Eagle Peak's lack of progress warranted a default termination.", "The agency's schedule rebuilds indicated potential delays."] | applies | [7, 21, 22]
Reasonableness of Termination Decision | Contract Disputes Act | Whether the contracting officer's decision to terminate was reasonable based on the circumstances at the time. | The government must prove that the termination decision was reasonable given the events that occurred before the termination. | The Board assessed the evidence and found that the CO's decision was not reasonable in light of Eagle Peak's progress and plans. | ['Eagle Peak had made significant progress and had plans to increase manpower.', "The CO's interpretation of the contract requirements was found to be incorrect."] | ["The CO had concerns about Eagle Peak's ability to meet the completion date.", "The agency's analysis indicated potential delays."] | applies | [14, 21, 22]
Contract Interpretation | Contract Language | How to interpret the contract clause regarding simultaneous site closures. | Contract interpretation begins with the plain language of the agreement, and all words must be given meaning. | The Board found that the CO's interpretation of the clause precluding simultaneous closures was incorrect, allowing for overlapping work as long as one site was open for public use. | ['The contract explicitly stated that sites could not be closed simultaneously but did not require one site to be fully completed before starting work on another.', "The definition of 'substantial completion' supports the interpretation that work could proceed as long as public access was maintained."] | ['The CO interpreted the clause to mean that all work must be completed at one site before starting at another.', "The agency's concerns about public access were valid."] | applies | [9, 10, 21]