## Fact Pattern
id | Fact
0 | In September 2020, DOI entered into a contract with QTI for bridge and road repair.
1 | The period of performance was September 23, 2020, to February 26, 2021.
2 | The contract incorporated Federal Acquisition Regulation (FAR) clause 52.242-14, Suspension of Work (APR 1984) (48 CFR 52.242-14 (2020)).
3 | To ensure that nesting birds were not disturbed, the contract prohibited QTI from performing masonry work on the bridge to be repaired between March 15 and September 1.
4 | On December 28, 2020, the contracting officer issued a unilateral modification, partially suspending work to address QTI’s mistake in price.
5 | DOI lifted the suspension on January 21, 2021.
6 | On February 4, 2021, the contracting officer issued another suspension and a cure notice, directing QTI to address several failures and deficiencies in its performance.
7 | After receiving several additional cure notices, QTI made the necessary adjustments, and the contracting officer lifted this second suspension on March 30, 2021.
8 | In April 2021, the parties executed a bilateral modification to address 'a mutual mistake in the contract price after award,' adding approximately $52,000 to the contract price.
9 | On January 4, 2022, the contracting officer issued two unilateral modifications.
10 | By letter dated January 10, 2022, QTI submitted a 'time and cost modification request,' seeking payment of $2000 per day for the period from March through November 2021, during which QTI alleged it was on standby due to 'latent conditions and changes' in a project that was 'not classified correctly.'
11 | In April 2022, QTI submitted a claim to the contracting officer pursuant to the contract’s Disputes clause, FAR 52.233-1, seeking payment of $481,109.75.
12 | On May 23, 2022, the contracting officer requested via email that QTI clarify the amount of its claim and provide documentation showing 'how [QTI] arrived at the amount claimed and explain to the Government why [QTI is] entitled to the sum amount claimed.'
13 | In its email reply the same day, QTI described a series of purported problems on the contract.
14 | The following day, the contracting officer and QTI exchanged a series of emails seeking to clarify the basis of QTI’s claim and the payment request for $75,840.25.
15 | On June 14, 2022, the contracting officer denied the claim, concluding that QTI had not provided support for its claim.
16 | In July 2022, QTI filed this appeal.
17 | After QTI submitted its complaint, DOI moved to partially dismiss the appeal for lack of jurisdiction because several of the allegations raised in the complaint were not presented to the contracting officer.
18 | In the Board’s March 2024 decision, Quality Trust, Inc. v. Department of Interior, CBCA 7451, 24-1 BCA ¶ 38,548, at 187,363, we held—based upon the correspondence between the contracting officer and QTI regarding the claim—that QTI’s claim was one for a period of standby in an amount of over $481,000.
19 | Following its March 2024 decision, the Board set a discovery schedule.
20 | After additional delays by QTI, DOI filed its motion for summary judgment in November 2024.
21 | The Board set a deadline for QTI to respond to DOI’s motion for summary judgment.
22 | The final deadline for QTI’s response was March 28, 2025.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Determining the relevance of evidence presented in the appeal. | The evidence regarding the contract modifications and claims made by QTI is relevant to the issues being adjudicated in the appeal. | The evidence directly relates to the performance and modifications of the contract, which are central to the dispute. | There may be arguments that some evidence is not directly related to the specific claims being made in the appeal. | admissible | [0, 1, 2, 4, 8, 10, 12, 14]
FRE 402 | General Admissibility of Relevant Evidence | Admissibility of evidence that is relevant to the case. | All relevant evidence presented by QTI regarding the contract and its modifications should be admissible unless otherwise excluded. | The evidence is relevant and not subject to exclusion under any other rules. | Potential objections may arise regarding the specificity or clarity of the evidence presented. | admissible | [0, 1, 2, 4, 8, 10, 12, 14]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Balancing the probative value of evidence against potential prejudice. | The evidence regarding QTI's claims and the contracting officer's responses must be weighed for its probative value against any potential for unfair prejudice. | The evidence is crucial for understanding the context of the claims and the contracting officer's decisions. | There may be concerns that the evidence could confuse the issues or mislead the Board regarding the claims. | depends | [10, 12, 14]
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Determining whether statements made in emails and correspondence are hearsay. | The emails exchanged between QTI and the contracting officer may be considered hearsay unless they fall under an exception. | The emails may be admissible as non-hearsay if they are offered to show the effect on the listener or for the truth of the matter asserted. | If offered for the truth of the matter asserted, the emails may be considered hearsay and thus inadmissible. | depends | [11, 13]
FRE 802 | The Rule Against Hearsay | Exclusion of hearsay evidence. | Any statements made in the emails that are offered for their truth may be excluded as hearsay. | If the statements are not offered for their truth but rather to show the context of the communications, they may be admissible. | Statements offered for their truth would be hearsay and inadmissible unless an exception applies. | depends | [11, 13]
FRE 803 | Exceptions to the Rule Against Hearsay | Identifying exceptions to hearsay for the emails exchanged. | Certain statements in the emails may qualify for exceptions to the hearsay rule, such as statements made by a party opponent. | If the emails contain statements made by QTI regarding its claims, they may be admissible under the party opponent exception. | If the statements do not meet the criteria for any exceptions, they may be excluded as hearsay. | depends | [11, 13]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Suspension of Work Clause | FAR 52.242-14 | Whether a contractor is entitled to an economic adjustment for a suspension of work. | A contractor shall receive an economic adjustment for any increase in contract performance costs necessarily caused by the unreasonable suspension, delay, or interruption of work by the contracting officer. | QTI claimed damages for standby due to suspensions issued by the contracting officer. The Board evaluated whether these suspensions were reasonable and if they were caused solely by DOI. | ['The contract explicitly incorporated FAR 52.242-14, which governs suspensions of work.', "QTI's claim was based on the assertion that the suspensions were unreasonable and caused by DOI."] | ["The suspensions were reasonable and necessary to address QTI's performance issues.", 'QTI agreed to certain restrictions at the outset of the contract, which negates claims of unreasonable suspension.'] | does not apply | [2, 3, 5, 6, 8, 9, 10]
Constructive Suspension Doctrine | P.R. Burke Corp. v. United States | Whether a contractor can claim for constructive suspension when work is stopped without an express order. | Constructive suspension occurs when work is stopped absent an express order by the contracting officer and the Government is found to be responsible for the work stoppage. | The Board determined that QTI's claim was for constructive suspension, but found that DOI was not the sole cause of the delays. | ["QTI alleged that its work was on standby due to DOI's mismanagement.", "The Board recognized the concept of constructive suspension in evaluating QTI's claims."] | ["The delays were caused by QTI's own performance issues and not solely by DOI.", 'The Board found that the suspensions were reasonable and justified.'] | does not apply | [8, 10, 11, 12, 13]
Eichleay Formula for Damages | P.J. Dick Inc. v. Principi | Whether a contractor can recover unabsorbed home office overhead using the Eichleay formula. | To establish entitlement to Eichleay damages, the contractor must show that there was a government-caused delay of uncertain duration, that the delay extended the original time for performance, and that the contractor was on standby and unable to take on other work during the delay. | QTI attempted to use the Eichleay formula to claim damages for standby, but failed to demonstrate that the delays were solely caused by DOI. | ["QTI claimed it was on standby due to DOI's actions.", 'The Eichleay formula is applicable for calculating unabsorbed overhead in cases of government-caused delays.'] | ['QTI agreed to the restrictions that caused the delays, negating the claim for Eichleay damages.', 'There was no period of delay solely attributable to DOI.'] | does not apply | [10, 11, 12, 13]