## Fact Pattern
id | Fact
0 | A contracting officer of the General Services Administration (agency) denied a certified claim of Boyd Atlanta Rhodes, LLC (lessor or Boyd) seeking an amount in excess of $3 million under a lease for a firm, ten-year term.
1 | The lessor maintained that the agency issued the notice to proceed, and accepted the space, on dates well beyond the time frame established in the lease.
2 | The lessor sought to be made whole for alleged Government breaches of the lease agreement, compensable delays, and constructive changes during the design-build phase of the lease which preceded acceptance of the space by the agency.
3 | The lessor attributes 401 days of delay to Government breaches.
4 | In October 2016, the agency entered into a lease agreement with a firm, ten-year lease term that would begin upon the substantial completion of the premises and the agency’s acceptance.
5 | Boyd became the eventual lessor under a lease amendment effective October 1, 2018, which incorporates a novation agreement signed by the agency and the leasing parties, entered into on June 26, 2018.
6 | A clause identifies the rent and other consideration the Government is to pay the lessor.
7 | The annual rent, $3,452,373.21, is the sum of shell rent, tenant improvement (TI) rent, operating costs, building specific amortized capital (BSAC) costs, and parking (at zero cost).
8 | The lease establishes a dollar amount as a tenant improvement allowance (TIA), amortized at zero interest over the lease term which the Government may use for TIs.
9 | The Government may spend in excess of the amount, reduce TI requirements, make lump sum payments, and/or decrease the rent to account for a lump sum payment.
10 | The lease contains a Rate for Adjustment for Vacant Leased Premises (SEP 2013) clause.
11 | The lease contains a No Waiver clause (SEP 1999), 48 CFR 552.270-26.
12 | As noted, the lease term begins with the agency’s acceptance of the premises.
13 | The lease agreement contains a construction schedule, commencing within five days after lease award, which 'shall be used' by the lessor and Government.
14 | The lessor is to provide design intent drawings (DIDs) within forty days.
15 | The Government has twenty days to review and approve the DIDs.
16 | Then, within twenty-five days, the lessor is to prepare and submit construction drawings with Government review to be completed within twenty days.
17 | The lessor then has forty days to prepare and submit the TI and BSAC price proposal with forty days for the Government’s review and approval.
18 | Within ten days thereafter, the Government is to issue the notice to proceed, and within the next 100 days, the lessor is to complete the work.
19 | Thus, the total workdays from lease award to Government acceptance is 295 days.
20 | As alleged by the lessor, the Government failed to meet several of its dates of performance; i.e., the Government (the agency or one of three tenant agencies) acted well in excess of the contract-defined time limits when it made determinations and changes to the design and other requirements, or simply failed to provide information necessary for the lessor’s progress.
21 | The alleged Government delays relate to the initial meetings, the formulation and approval of design intent drawings, various iterations of construction drawings and TI and BSAC price proposals, selection of a design that would come within budget, and the issuance of the notice to proceed.
22 | All of these actions were required for the lessor to complete the building spaces such that the agency could accept the spaces which would trigger the rent commencement date.
23 | The lessor periodically submitted revised construction schedules, which the agency approved.
24 | The lessor contends that, taking into account its delays, the agency was responsible for 401 days of delay, which required the lessor to expend additional time and effort to obtain the notices to proceed and to complete the space to allow for acceptance and occupancy.
25 | Effective April 9, 2019, lease amendments contained notices to proceed with construction and alterations for three tenant spaces in the building.
26 | The amendments established dollar lump sum pricing (not to be exceeded) for TIs and BSAC improvements with all work to be substantially complete by December 9, 2019.
27 | With substantial completion achieved, the agency accepted the spaces by bilateral lease amendment, effective May 6, 2020.
28 | Rental payments began under the terms of the lease.
29 | The amendment established rates (shell, operating costs, TIA, BSAC, parking) for the rent of the spaces with a total annual rent of $3,461,692.26; the lessor reserved its rights to pursue recovery of increased costs and/or damages.
30 | The lessor submitted its certified claim to the contracting officer.
31 | The lessor sought $3,171,372.85, arising from the Government’s alleged breach of contract, compensable delays, and constructive changes.
32 | The contracting officer denied the claim, stating that it is well established that lost rent is not recoverable for a government-caused delay.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Determining the relevance of evidence related to the lease agreement and alleged delays. | The evidence regarding the timeline of events and the actions of both the lessor and the agency is relevant to establish whether the agency's actions caused delays that justify the lessor's claims. | The timeline and actions of the agency are directly related to the lessor's claims of breach and delays, making them relevant to the case. | Some evidence may be deemed irrelevant if it does not directly pertain to the specific claims made by the lessor. | admissible | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
FRE 402 | General Admissibility of Relevant Evidence | General admissibility of evidence related to the lease and alleged breaches. | All relevant evidence regarding the lease agreement and the actions of the agency and lessor should be admissible unless otherwise excluded. | The evidence is relevant to the claims and defenses in the case, thus should be admitted. | Potentially prejudicial evidence may be excluded if it confuses the issues or misleads the jury. | admissible | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Balancing the probative value of evidence against potential prejudice. | While the evidence is relevant, it must be weighed against the risk of unfair prejudice or confusion of the issues. | The evidence is crucial for understanding the timeline and responsibilities of both parties, which outweighs any potential prejudice. | Some evidence may be overly complex or confusing, leading to potential misinterpretation by the jury. | depends | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
FRE 404 | Character Evidence; Crimes or Other Acts | Use of evidence regarding the agency's prior conduct in relation to the lease. | Evidence of the agency's past conduct may be relevant to establish a pattern of behavior that supports the lessor's claims. | If the agency's past actions demonstrate a consistent pattern of delays or breaches, this evidence may be admissible to show intent or motive. | Such evidence may be seen as character evidence that is inadmissible to prove action in conformity therewith. | depends | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Determining whether statements made by the agency or lessor constitute hearsay. | Statements made by the agency regarding the lease and its performance may be considered hearsay unless they fall under an exception. | Certain statements may be admissible as non-hearsay if they are offered for a purpose other than the truth of the matter asserted. | If statements are offered to prove the truth of the matter asserted, they may be excluded as hearsay. | depends | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]
FRE 802 | The Rule Against Hearsay | General rule against hearsay evidence. | Any evidence that is considered hearsay will be inadmissible unless it falls under an exception. | If the evidence can be categorized under a hearsay exception, it may be admissible. | Most statements made by the agency or lessor regarding the lease's performance may be hearsay and thus inadmissible. | inadmissible | [0, 1, 3, 4, 5, 8, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Lost Rent Recovery Rule | Coley Properties Corp. v. United States, 593 F.2d 380 (Ct. Cl. 1979) | Whether lost rent is recoverable for delays caused by the government. | Lost rent due to government-caused delays is not recoverable as it does not constitute a cost of performance under the contract. | The lessor seeks to recover lost rent for the period before the agency accepted the premises, but the court finds that the lease term had not commenced, and thus no rent was due. | ['The lease specifies that rent payments begin only upon acceptance of the premises.', 'Case law establishes that lost income is not considered a cost of performance.'] | ["The lessor argues that the government's actions constituted breaches that should allow for recovery of lost rent.", 'The lessor contends that the delays caused by the government were outside the scope of the Changes clause.'] | does not apply | [0, 1, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34]
Cardinal Change Doctrine | Rumsfeld v. Freedom NY, Inc., 329 F.3d 1320 (Fed. Cir. 2003) | Whether the government's changes to the project constituted a cardinal change to the lease. | A cardinal change occurs when the government alters the work so drastically that it requires the contractor to perform duties materially different from those originally bargained for. | The lessor claims that the government's actions extended the pre-occupancy period significantly, which may constitute a cardinal change. | ['The lessor asserts that the government made changes that went beyond the scope of the lease.', 'The extended delays and changes in requirements could be seen as altering the fundamental nature of the contract.'] | ['The agency argues that it has the unrestricted ability to make changes prior to occupancy without being in breach.', 'The agency contends that the changes were within the scope of the lease and did not constitute a cardinal change.'] | uncertain | [0, 1, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34]
Changes Clause Interpretation | FAR 52.243-4 | Whether the changes made by the government fall under the Changes clause of the lease. | The Changes clause allows the contracting officer to direct changes to the work, but such changes must be within the general scope of the contract. | The lessor argues that the government's changes were not limited to tenant improvements and thus could constitute breaches of the lease. | ['The lease specifies that changes can be made, but the lessor contends that the changes exceeded what was allowed.', 'The lessor claims that the changes affected the fundamental aspects of the lease agreement.'] | ['The agency maintains that it acted within its rights under the Changes clause.', 'The agency argues that all changes were necessary and within the scope of the lease.'] | uncertain | [0, 1, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34]