## Fact Pattern
id | Fact
0 | On September 5, 2019, FWS issued a statement of work (SOW) for design-build services to rehabilitate two existing parking areas and add a new graveled parking area at the Arthur R. Marshall Loxahatchee National Wildlife Refuge in Boynton Beach, Florida.
1 | On May 20, 2020, FWS issued amendment 1 to the SOW which (1) increased the length of Lee Road to be rehabilitated; (2) added restriping of existing parking lots; and, relevant to the dispute here, (3) increased from 24,000 square feet (sq. ft.) to 54,222 sq. ft. the area of the Hillsboro parking lot that need to be rehabilitated.
2 | On June 25, 2020, CEI submitted its bid schedule to FWS.
3 | In July 2020, FWS awarded the contract to CEI, accepting CEI’s bid schedule for a total price of $389,630.
4 | SOW section 6, entitled 'Specific Project Requirements,' contains a subsection c., entitled 'Permit Application Assistance.'
5 | On September 23, 2020, FWS and CEI entered into bilateral modification P00001 (mod 1) to include construction services costs for rehabilitating the boat access ramp area.
6 | In a letter dated March 16, 2021, FWS first applied for a permit to the South Florida Water Management District (SFWMD).
7 | On April 7, 2021, SFWMD inspected the project site.
8 | On April 14, 2021, SFWMD stated, 'It appears that the L-39 levee does not meet the minimum design cross section requirements at this location.'
9 | On May 10, 2021, modification P00002 (mod 2), valued at $64,648.20, was created for 'construct[ing] Hillsboro drain pipe & curb' and 'Lee Road centerline paint striping.'
10 | CEI was onsite between contract award and mod 2, but construction had not commenced because of permitting delays.
11 | On May 16 and July 15, 2021, SFWMD exchanged internal emails about the levee needing to 'be brought to minimum with select fill then the gravel be added on top of that.'
12 | On June 4, 2021, SFWMD directed CEI to revise the drawings, which caused an increase of the overall levee elevations.
13 | On July 22, 2021, modification P00003 (mod 3) added 'construction services to repave the remainder of Lee Road to the refuge’s eastern boundary,' 'install 3 speed tables along Lee Road,' and 'accept contractor proposal.'
14 | On August 11, 2021, SFWMD issued the permit to FWS.
15 | On August 20, 2021, SFWMD, on behalf of FWS, submitted a section 408 permit application to the United States Army Corps of Engineers (USACE).
16 | In a November 1, 2021, letter, the engineering division of USACE advised SFWMD that it had completed its technical review and that the FWS request was approved.
17 | In a July 29, 2022, letter, USACE’s regulatory division advised FWS that it was granting permit approval in response to FWS’s August 2021 application.
18 | In modification P00004, signed by CEI on August 25, 2021, FWS extended the project’s completion date to December 31, 2021, due to SFWMD’s delays in conducting permitting authority reviews for permit approval.
19 | In undated modifications P00005 and P00006, FWS unilaterally further extended the completion date to September 30, 2022, and then to December 31, 2022, due to extensive permit application delays of SFWMD and USACE.
20 | On August 3, 2022, SFWMD advised FWS that the USACE permit had been approved and directed an onsite preconstruction meeting.
21 | On August 17, 2022, the preconstruction meeting was conducted onsite.
22 | CEI’s work on the project was performed from August 2022 to January 2023.
23 | On January 23, 2023, CEI submitted a change order request for the additional work and associated costs caused by the scope of work changes required by the SFWMD permit.
24 | CEI claims that instead of its originally anticipated quantity of approximately 1863 tons of road base material required for the project, it actually placed 3370 tons of material.
25 | On March 6, 2023, FWS denied CEI’s change order request.
26 | On March 16, 2023, CEI submitted its certified claim for $106,060.78 to FWS.
27 | On April 28, 2023, before FWS rendered any decision on the claim, CEI submitted a revised damages calculation of $137,736.03.
28 | On July 12, 2023, FWS denied the claim.
29 | On May 17, 2023, CEI filed a notice of appeal.

## Rules of Evidence
rule_number | rule_title | issue | application | arguments_for_admissibility | arguments_against_admissibility | likely_admissibility | triggering_facts
FRE 401 | Test for Relevant Evidence | Determining the relevance of evidence related to the project timeline and modifications. | The timeline of events and modifications to the contract are relevant to understanding the context of CEI's claims and FWS's decisions. | The sequence of events provides necessary context for the claims made by CEI and the actions taken by FWS, which are central to the dispute. | Some evidence may be seen as overly detailed or tangential, potentially confusing the jury about the main issues. | admissible | [0, 1, 3, 4, 5, 6, 8, 10, 12, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26]
FRE 403 | Exclusion of Relevant Evidence on Grounds of Prejudice, Confusion, or Waste of Time | Balancing the probative value of evidence against potential prejudice or confusion. | While the evidence is relevant, there may be concerns about overwhelming the jury with details that do not directly pertain to the core issues of the case. | The evidence is crucial for establishing the timeline and understanding the context of the claims. | The sheer volume of evidence may lead to confusion or distract from the main issues at hand. | depends | [0, 1, 3, 4, 5, 6, 8, 10, 12, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26]
FRE 406 | Habit; Routine Practice | Evidence of CEI's routine practices in project execution. | Evidence of CEI's typical practices in similar projects may be relevant to establish their claims regarding the additional work and costs incurred. | Demonstrating CEI's routine practices can help establish a baseline for what was expected in the project. | The evidence may not be sufficiently established as a habit or routine practice that is relevant to the specific project in question. | depends | [1, 3, 12, 13, 14, 15, 16, 17, 18]
FRE 801 | Definitions That Apply to This Article; Exclusions from Hearsay | Determining whether certain statements made by SFWMD or FWS are hearsay. | Statements made by SFWMD regarding the levee and permit approvals may be considered hearsay unless they fall under an exception. | If the statements are offered for their truth and fall under a hearsay exception, they may be admissible. | Many statements may be considered hearsay and not admissible unless an exception applies. | depends | [8, 9, 10, 11, 12, 13, 14, 15]
FRE 803 | Exceptions to the Rule Against Hearsay – Regardless of Whether the Declarant Is Available as a Witness | Applying hearsay exceptions to statements made by SFWMD and USACE. | Certain statements made by officials regarding the project and permits may qualify as exceptions to the hearsay rule. | Statements made by public officials in their official capacity may be admissible under the public records exception. | Some statements may not meet the criteria for the exceptions and could be excluded as hearsay. | depends | [8, 9, 10, 11, 12, 13, 14, 15]

## Substantive Rules
rule_label | rule_source | legal_issue | rule_summary | application | supporting_arguments | counter_arguments | likely_outcome | triggering_facts
Permitting Responsibility | FAR 52.236-7 | Whether the contractor bears the risk for additional costs arising from permitting requirements. | The government is responsible for obtaining necessary permits, while the contractor's role is to assist in the process. | CEI's contract required it to assist FWS in obtaining permits, and FWS was responsible for the permitting process, which included the SFWMD and USACE permits. | ['FWS was the party responsible for obtaining the permits.', "CEI's responsibility was limited to assisting in the permit application process."] | ['FWS argues that CEI should have anticipated the permitting requirements and associated costs.'] | applies | [0, 1, 5, 6, 8, 11, 12, 14]
Change Order and Scope of Work | Contract Disputes Act | Whether CEI is entitled to additional compensation for work beyond the original contract scope. | Contractors may be entitled to compensation for changes in the scope of work that were not anticipated at the time of bidding. | CEI claims that the requirement to raise the levee elevation was not anticipated and constituted a change in the scope of work, justifying a change order request. | ["CEI's bid anticipated a specific quantity of material, which was exceeded due to the new requirements.", 'The changes were mandated by the permitting authority and were beyond what was originally agreed upon.'] | ['FWS contends that CEI should have foreseen the need for additional work based on the project requirements.'] | applies | [19, 20, 21, 22]
Compensable Delay | FAR 52.233-1(h) | Whether CEI is entitled to recover costs due to delays caused by the government. | Contractors may recover costs associated with delays that are attributable to the government. | CEI alleges that the delays in obtaining permits caused increased costs, which may be compensable under the contract. | ["The delays were caused by the permitting authorities, which are under the government's control.", 'CEI incurred additional costs due to the extended timeline and increased material prices.'] | ['FWS argues that CEI should bear the risk of cost increases under a firm-fixed-price contract.'] | applies | [14, 15, 16, 17, 18]